## Summary
WordPress Plugin — Quote Management Tool Revised Estimation (70-Hour MVP + Homeowner Dashboard)
ChangeFluent Ltd · Fixdly.com
Project | Quote Management Tool — Custom WordPress Plugin
Client / Owner | ChangeFluent Ltd
Primary Brand | Fixdly.com (reusable: LeafAndLush.com)
Estimation Date | 27 Feb 2026
Approach | Custom WordPress plugin — no Google Docs / Zapier / SendGrid API for MVP
PDF Generation | Plugin-native (eliminates Google Docs dependency)
Homeowner Access | Guest query submission — no homeowner account required for MVP
Subscription Model | Starter: 10 quotes/mo · 5 iter max ¦ Pro: 40 quotes/mo · 10 iter max
Total Budget Cap | 70 hours
Phase Summary — Hour Allocation (70-Hour MVP)
Phase | Module | Hours
P1 | Plugin Core, Data Model & Subscription Tiers | 5
P2 | Trade Category & Geo-Matching Engine | 4
P3 | Quote Builder (Tradesperson Toolbox) | 11
P4 | Homeowner Guest Query & Quote Portal | 8
P5 | Amendment Engine & Iteration Limit Control | 5
P6 | Versioning, Audit Trail & Native PDF Export | 6
P7 | Stripe Deposit Payment Integration | 6
P8 | Email Notifications | 4
P9 | Trades Pipeline Dashboard | 5
P10 | Homeowner Dashboard (NEW) | 10
P11 | QA, Testing & Deployment | 6
TOTAL | All Phases (11) | 70
✓ Total = 70 hours — within the 70-hour revised budget cap.

## Detailed Estimation
ChangeFluent — Quote Management Tool ¦ Detailed Estimation (70-Hr MVP) ¦ Feb 2026
# | Phase | Feature / Module | Scope (what is built) | Hours
PHASE 1 — Plugin Core, Data Model & Subscription Tiers [5 hrs]
1 | P1 | Plugin bootstrap & CPT registration | Plugin init, activation hooks, autoloader. CPTs: Quote, QuoteArea, Customer, TradeProfile, HomeownerQuery. Meta key definitions. | 1.5
2 | P1 | Subscription tier config (Starter / Pro) | PMS membership mapping: Starter → 10 quotes/mo, 5 iter max; Pro → 40 quotes/mo, 10 iter max. Enforce limits on quote creation and amendments. | 1.5
3 | P1 | Branding & multi-brand config layer | Settings API: brand name, industry wording, logo, accent colour. Filterable constants for Fixdly vs LeafAndLush reuse. | 1.5
4 | P1 | Trade category register (non-hierarchical) | ~20 flat categories (Carpenter, Electrician, Plumber…). Admin-editable list. No sub-groupings for MVP. | 0.5
PHASE 2 — Trade Category & Geo-Matching Engine [4 hrs]
5 | P2 | Tradesperson geo-radius profile field | Add postcode + work radius (miles) to TradeProfile. Stored and indexed for query matching. | 0.5
6 | P2 | Query-to-tradesperson matching logic | On new homeowner query: filter TradeProfiles by category + homeowner postcode within declared radius. Rank by activity score. Cap at top 10. | 2
7 | P2 | Response cap enforcement (first 3–5 rule) | Track quote responses per query. Lock to new responders at cap (3–5). Status → 'Quotes Full'. Notify late responders. | 1.5
PHASE 3 — Quote Builder (Tradesperson Toolbox) [11 hrs]
8 | P3 | Toolbox shell (basic — full dashboard in P9) | Subscriber-gated Toolbox. Minimal shell with route to Pipeline dashboard (P9). Navigation between sections. | 1
9 | P3 | Quote Builder — Step 1: Customer details | Enter/select customer (name, email, phone). Guest homeowner token link generated — no account required. | 1
10 | P3 | Quote Builder — Step 2: Area/Room builder | Add/edit/remove areas. Per-area: name, scope (rich text), price, Included/Optional flag, validity date, materials, labour hrs, photo upload. | 3
11 | P3 | Quote Builder — Step 3: Totals & settings | Auto-calculated subtotal, VAT toggle, deposit % or 'no deposit' option, iteration limit (within plan max), grand total. Save as Draft. | 1.5
12 | P3 | Native PDF export (plugin-generated) | Generate branded PDF internally (TCPDF/DomPDF). Trade logo, all areas+scope, totals, version number, issue date, validity. No Google Docs required. | 2.5
13 | P3 | Secure token link & quote send | Generate cryptographic token. Build customer portal URL. Send email with token link + PDF. Log 'Sent' event. Status → SENT. | 1
14 | P3 | Direct quote entry (Route B — no lead) | Tradesperson can start a quote directly from Toolbox without an inbound Fixdly lead. | 1
PHASE 4 — Homeowner Guest Query & Quote Portal [8 hrs]
15 | P4 | Homeowner guest query submission form | Public form (no login): job description, trade category, postcode, contact details. Triggers geo-matching → distributes to top 10. Captures details for marketing. | 2
16 | P4 | Customer Quote Portal — token validation & display | Validate token + expiry. Display quote summary, trade branding, all areas with scope/price/validity. Responsive layout. | 2
17 | P4 | Area selection & partial acceptance | Select/deselect optional areas. Included areas pre-selected and locked. Live total recalculation. | 1.5
18 | P4 | E-sign, Accept & Decline flows | Typed e-signature + date. Accept → APPROVED/PARTIAL, log event, notify tradesperson. Decline → DECLINED, log event. PDF download. | 1
19 | P4 | Response-cap re-open on full rejection | If homeowner rejects all submitted quotes, system re-opens query to remaining top-10 pool. | 1
20 | P4 | Portal expiry & invalid token handling | Show 'Quote Expired' or 'Invalid Link' notices. Log expiry event via WP Cron. | 0.5
PHASE 5 — Amendment Engine & Iteration Limit Control [5 hrs]
21 | P5 | Amendment request form (customer-facing) | Tick-box interface: mark areas to add/remove. Message window for context. Submit blocked if iteration_used == iteration_limit. | 1.5
22 | P5 | Iteration limit enforcement & counter | iteration_used++ on each customer-triggered reissue. Block at limit. Trade can reset within plan max. Counter shown in dashboard. | 1
23 | P5 | Tradesperson amendment review & reissue | Dashboard shows pending requests + tick-box summary. Options: Reissue (new version), Reject (message), Approve as-is. | 2
24 | P5 | Amendment status notifications | Notify homeowner of rejection with message. Notify trade of new amendment request. Log all events. | 0.5
PHASE 6 — Versioning, Audit Trail & Native PDF [6 hrs]
25 | P6 | Quote versioning system | Version field (v1.0, v1.1…). Snapshot state on reissue. Always-latest token link (agreed default). Version in UI + PDF. | 1.5
26 | P6 | Audit trail / Events log | Events table: event_id, timestamp, quote_id, version, actor_type, actor_id, event_type. All key events logged. | 2
27 | P6 | PDF versioning (plugin-native) | Each version regenerates PDF with version number + issue date. Stored per version. No third-party dependency. | 2
28 | P6 | WP Cron: expiry & reminder scheduling | 48h after sent (if unviewed) + 24h before expiry reminders. Log reminder events. | 0.5
PHASE 7 — Stripe Deposit Payment Integration [6 hrs]
29 | P7 | Deposit rules configuration (tradesperson) | Per-quote deposit: % (0–100%) or 'No deposit required'. Calculated on selected areas total. Set in Quote Builder Step 3. | 0.5
30 | P7 | Stripe payment link generation | On acceptance, generate Stripe Payment Link via API. Store link. Surface 'Pay Deposit' button on portal. | 2
31 | P7 | Stripe webhook handler | WordPress REST endpoint. Verify signature. Handle payment_intent.succeeded. Status → PAID. Log event. Notify trade. Idempotency check. | 2
32 | P7 | Stripe test mode & staging config | Test/live key toggle in plugin settings. Stripe CLI webhook test. Staging smoke test. | 1
33 | P7 | Deposit confirmation display on portal & dashboard | Show 'Deposit Paid' badge on customer portal and homeowner dashboard. Update Trades 'Awaiting Deposit' tab. | 0.5
PHASE 8 — Email Notifications [4 hrs]
34 | P8 | Plugin-native email templates | Transactional emails via wp_mail() + SMTP plugin. Templates: Query Received, Quote Sent, Viewed, Amendment Requested, Reissued, Accepted, Deposit Paid, Expiry Reminder, Dashboard Magic Link. | 2.5
35 | P8 | Notification trigger hooks | WordPress action hooks on each status transition. Fires correct template with dynamic variables. | 1
36 | P8 | Late-responder quota-full notification | When response cap hit, notify remaining tradespeople query is closed. Update job status. | 0.5
PHASE 9 — Trades Pipeline Dashboard [5 hrs]
37 | P9 | Trades Dashboard — Pipeline view | Table: Customer, Job desc, Status badge, Iteration count (x/n), Last activity, Query source. Sortable. Stat cards: quotes this month, win rate, avg time to approve. | 2.5
38 | P9 | Trades Dashboard — Amendments tab | Pending amendment requests with iteration fraction + Review CTA. Quick-review inline. | 1
39 | P9 | Trades Dashboard — Awaiting Deposit tab | Accepted quotes with deposit unpaid. Deposit amount display. Copy payment link button. | 1
40 | P9 | Activity/priority score (basic) | Simple score: last-active timestamp + response rate. Tie-breaker for top-10 query distribution. Admin-visible on TradeProfile. | 0.5
PHASE 10 — Homeowner Dashboard (10 hrs)
41 | P10 | Magic-link authentication for homeowners | Homeowner requests magic link via email address. System emails a time-limited login link. No password required. Sessions scoped to that email. Secure token generation and validation. | 1.5
42 | P10 | Dashboard shell — quotes list view | Authenticated homeowner sees all quotes tied to their email. Grouped by tradesperson/provider. Status badges: Sent, Approved, Partial, Pending Amendment, Deposit Paid, Expired. Sorted by last activity. | 2
43 | P10 | Project grouping (optional label) | Optional project label field on query (e.g. 'Home Extension', 'Kitchen Refurb'). Homeowner can assign/edit label. Quotes grouped by project on dashboard with count and summary status. | 1.5
44 | P10 | Quote detail view (from dashboard) | Open any quote from dashboard into the Customer Quote Portal (existing P4 view). Back button returns to dashboard. Shows current version with version history indicator. | 1
45 | P10 | Multi-quote comparison view | Side-by-side or stacked comparison of 2–3 quotes for the same project. Compare: tradesperson name, areas covered, total price, validity, deposit requirement, status. Highlight cheapest / fastest to respond. | 2
46 | P10 | Status filter & search bar | Filter quotes by status (All / Approved / Pending / Sent / Expired). Search by tradesperson name or job description. Instant client-side filtering. | 1
47 | P10 | Request another quote (re-submit query) | CTA on dashboard to submit a new guest query for a different project or to get more quotes for an existing one. Pre-fills category and project label from history. | 1
PHASE 11 — QA, Testing & Deployment [6 hrs]
48 | P11 | Core logic unit tests | PHPUnit: iteration enforcement, token validation, response cap, deposit calculation, geo-match filter, magic-link auth, status transitions. | 2
49 | P11 | End-to-end journey testing (5 flows) | Manual QA: Flow A (guest query+matching), Flow B (quote builder+send), Flow C (portal review+sign), Flow D (amendment+reissue), Flow E (deposit). + Homeowner dashboard journey. | 2
50 | P11 | Deployment, docs & handover | Staging → production deploy. Plugin README. Admin setup guide (Stripe, SMTP, PMS). Handover session. | 2
GRAND TOTAL — ALL PHASES (Target: 70 hrs) |  |  |  | 70

## Sprint Plan
Sprint Plan — 4 × 2-Week Sprints (8 Weeks) ¦ 70-Hour Budget
Sprint | Deliverables | Phases | Hours | Cumulative
Sprint 1 Weeks 1–2 | Plugin bootstrap, CPTs (incl. HomeownerQuery), meta schema, subscription tier config (Starter/Pro). Trade category register. Branding config layer. Quote Builder Steps 1–2 (customer entry, area/room builder with Included/Optional flags, scope rich text, photo upload). Geo-radius profile field + top-10 matching engine. Response cap enforcement (first 3–5 rule). Homeowner guest query form. Route B direct quote entry. | P1, P2, P3 (partial) | 18 | 18
Sprint 2 Weeks 3–4 | Quote Builder Step 3 (totals, VAT, deposit rules, iteration limit). Native PDF export (plugin-generated). Secure token link + wp_mail() send. Customer Quote Portal (token validation, area display, partial selection, e-sign, accept/decline, expiry handling). Response-cap re-open logic. Amendment tick-box form + iteration enforcement. Tradesperson amendment review + reissue. Quote versioning (v1.x). Audit trail events log. PDF versioning. WP Cron reminders. Amendment notifications. | P3 (complete), P4, P5, P6 | 22 | 40
Sprint 3 Weeks 5–6 | Stripe deposit rules + Payment Link generation. Stripe webhook (idempotency, PAID, logging). Deposit confirmation on portal + dashboard. Plugin-native email (9 templates + trigger hooks incl. magic-link email). Late-responder quota notifications. Trades Pipeline Dashboard (pipeline, amendments, awaiting deposit tabs). Activity priority score. HOMEOWNER DASHBOARD: Magic-link auth, quotes list view, project grouping, quote detail view, multi-quote comparison, status filter/search, re-submit query CTA. | P7, P8, P9, P10 | 22 | 62
Sprint 4 Weeks 7–8 | PHPUnit core logic tests (iteration, token, response cap, deposit calc, magic-link auth, status transitions). End-to-end QA: all 5 flows + homeowner dashboard journey. Mobile + desktop testing (Chrome, Safari). Stripe CLI webhook testing. Bug fixes. Staging → production deployment. Plugin README + admin setup guide. Handover session. | P11 | 8 | 70
TOTAL |  |  | 70 | 70

## Scope Decisions
Scope Decisions — In-Scope vs Out-of-Scope for 70-Hour MVP
# | Status | Item | Rationale / Source
1 | IN | Custom WordPress plugin (not standard plugins only) | Meeting: Pranav recommends custom plugin for doc management, versioning, email. Gareth agreed.
2 | IN | Native PDF generation (plugin-internal, no Google Docs) | Meeting: Google Docs questioned. Pranav confirmed plugin handles PDF natively. ~6–10 hrs saved.
3 | IN | Homeowner guest query — no registration for MVP | Meeting: Gareth + Pranav agreed. Homeowners submit as guest. Details captured for marketing.
4 | IN | Subscription tiers: Starter (10 quotes, 5 iter) + Pro (40 quotes, 10 iter) | Meeting: Gareth confirmed both tiers and limits.
5 | IN | Top-10 query distribution + first 3–5 response cap | Meeting: prevents overwhelm, creates urgency, practical for MVP.
6 | IN | Tradesperson-defined deposit rules (incl. zero deposit option) | Meeting: tradesperson sets own rules. Single holding payment only.
7 | IN | Flat trade categories (~20, non-hierarchical) | Meeting: keep simple. No sub-groupings, no multi-trade job grouping.
8 | IN | Audit trail: event_id, timestamp, quote_id, version, actor_type, actor_id | Meeting: fields confirmed for dispute protection and future migration.
9 | IN | Amendment tick-box + message window | Meeting: tick boxes for optional items + free-text message.
10 | IN | Plugin-native email via wp_mail() (no SendGrid API for MVP) | Meeting: removes third-party dependency. SendGrid is trivial post-MVP swap.
11 | IN | Homeowner Dashboard (Phase 10 | Added in this revision. Magic-link auth, quotes list, project grouping, comparison, filter, re-submit.
12 | IN | Magic-link authentication for homeowner dashboard | No account/password needed. Secure HMAC-signed time-limited link. Consistent with guest model.
13 | IN | Multi-quote comparison view | PRD requirement: homeowner needs to compare quotes by provider. Highlight lowest price + fastest.
14 | OUT | Google Docs API integration for PDF
15 | OUT | Zapier automation flows
16 | OUT | SendGrid API integration
17 | OUT | Full homeowner account registration & saved profile
18 | OUT | Multi-trade job grouping
19 | OUT | Reviews / ratings system
20 | OUT | LeafAndLush.com brand activation in MVP
21 | OUT | Canvas drawn e-signature
22 | OUT | Subsequent payment management (beyond deposit)
23 | OUT | Automated GDPR cleanup tools

## Subscription Tiers
Subscription Tier Specification — Starter & Pro (confirmed in meeting)
# | Feature / Parameter | Starter | Pro
1 | Monthly quote allowance | 10 quotes / month | 40 quotes / month
2 | Max iterations per quote | 5 iterations | 10 iterations
3 | What counts toward iteration limit | Customer-triggered amendments only | Customer-triggered amendments only
4 | Tradesperson can override iteration cap | Yes — within plan max | Yes — within plan max
5 | Quote builder access | Full access | Full access
6 | Native PDF generation | Yes | Yes
7 | Area/room breakdown (Included + Optional) | Yes | Yes
8 | Deposit rules (own-defined, incl. zero) | Yes | Yes
9 | Geo-matching & query distribution | Top 10 pool | Top 10 pool + priority boost
10 | Response cap per query | First 3–5 to respond | First 3–5 to respond
11 | Audit trail | Yes | Yes
12 | Stripe deposit payment | Yes | Yes
13 | Plugin-native email notifications | Yes | Yes
14 | Trades Pipeline Dashboard | Full | Full
15 | Homeowner Dashboard (magic-link) | Homeowner receives magic link | Homeowner receives magic link
16 | Multi-quote comparison view | Up to 3 quotes | Up to 3 quotes
17 | Project grouping on dashboard | Optional label | Optional label
18 | Activity/priority score | Basic | Enhanced (post-MVP)
19 | Reviews / ratings | Post-MVP | Post-MVP
20 | Multi-brand config (LeafAndLush) | Post-MVP | Post-MVP
21 | API access | Not included | Post-MVP